## Sheet1
Annex 5 Implementation Timetable
Project/Programme Title:
COMPONENTS/OUTPUTS | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1
1.1 A Regional Climate Centre and frameworks for Climate Services (CS) established in the SWIO region
1.1.1 Develop regional and national frameworks for climate services (RFCS & NFCS) | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Institutional and organisational framework consultation; 2022 Q2: Institutional and organisational framework consultation; 2022 Q3: Institutional and organisational framework consultation; 2022 Q4: Institutional and organisational framework signed
1.1.2 Design the legal, institutional, financial and organisational strategy to establish the RCC within IOC | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: Climate services strategy signed
1.1.3 Design the strategy of the regional lab for maintenance and annual calibration of equipment, and the strategy of the regional training lab (both labs will be set up under Output 2.2) | 2021 Q4: Strategic Plan; 2022 Q1: Strategic Plan; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Regional Lab and Regional training strategy signed
1.1.4 Prepare a strategy to improve Regional Numerical Weather Prediction | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: NWP strategy signed
1.2 Institutional arrangements and operational strategy of national met. services strengthened
1.2.1 Develop and implement a plan to strengthen institutional settings of NHMSs Strengthen the institutional, operational and financial strategy of NHMSs for each target country | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: Legal and Regulatory framework consultation; 2023 Q3: First SOP operational with the other institutions; 2024 Q2: Second SOP operational; 2025 Q1: Third SOP operational
1.2.2 Develop a business plan for each NHMS Design the transition support plan of each NHMS, DRR institutions and relevant sectoral ministries | 2021 Q3: Strategic Plan; 2021 Q4: Strategic Plan; 2022 Q1: Legal and Regulatory framework consultation; 2022 Q2: Legal and Regulatory framework consultation; 2022 Q3: Legal and Regulatory framework consultation; 2022 Q4: Legal and Regulatory framework consultation; 2023 Q1: Legal and Regulatory framework consultation; 2023 Q2: Business and transition plans signed
1.3 Improved staffing of the RCC and national met. Services
1.3.1 Recruit new staff members for the RCC and meteorological services | 2021 Q3: Staffing Plan; 2021 Q4: Staffing Plan; 2022 Q1: Recruitment; 2024 Q1: Recruitment
1.3.2 Train/update training for new/existing staff |  |  | Training Plan | Training Plan | Initial training for technicians and engineers for two and three years respectively |  | Information managment workshop | Analysis workshop | GIS workshop | Remote sensing workshop | Information managment workshop | Analysis workshop | Initial training for technicians and engineers for two and three years respectively | Remote sensing workshop | Information managment workshop | Analysis workshop | GIS workshop | Remote sensing workshop
1.4 Detailed Design, technical specification, system integration and tendering process of Project Activities
1.4.1. Produce a detailed design and system integration for each met service |  | NMHSs systems design | NMHSs systems design | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implemen-tation | Support implementation | Support implementation
1.4.2 Ensure that all systems installed are properly integrated within each other using data from the observing stations to the end-users production |  | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | NMHS systems integration plan | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implementation | Support implemen-tation | Support implementation | Support implementation
Component 2
2.1 Enhanced hydro-meteorological observing, monitoring, and impact forecasting services
2.1.1 Modernise/upgrade climate observation and monitoring network |  |  |  | Procurement of hardware | Procurement of hardware | Procurement of hardware | Installation | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.1.2 Modernise/upgrade information system for telecom, forecast, climatology |  |  |  | Procurement of software | Procurement of software | Procurement of software | Installation | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.2 Regional facilities for maintenance and training established
2.2.1 Establish maintenance lab | [7 empty] | Procurement of hardware | Procurement of hardware | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.2.2 Refurbish regional training centre of Mauritius to train observers and forecasters | [7 empty] | Procurement of hardware and software | Procurement of hardware and software | Installation | Installation | Support | Support | Support | Support | Support | Support | Support | Support | Support
2.3 R&D capacities enhanced to improve understanding of climate and disaster risks on communities and sectors
2.3.1 Organise training to improve downscaling of meteorological data | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Specific R&D training for engineers for one year; 2023 Q1: Specific R&D training for engineers for one year; 2024 Q1: Specific R&D training for engineers for one year; 2025 Q1: Specific R&D training for engineers for one year
2.3.2 Organise training and R&D activities on climate modelling capacity | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Specific R&D training for engineers for one year; 2023 Q1: Specific R&D training for engineers for one year; 2024 Q1: Specific R&D training for engineers for one year; 2025 Q1: Specific R&D training for engineers for one year
2.3.3 Organise training on hydrologic modelling for flood prevision (i.e. flood propagation model) | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Specific R&D training for engineers for one year; 2023 Q1: Specific R&D training for engineers for one year; 2024 Q1: Specific R&D training for engineers for one year; 2025 Q1: Specific R&D training for engineers for one year
2.3.4 Organise training to produce seasonal agrometeorological bulletins downscaled at national, regional and local level (if possible) | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Specific R&D training for engineers for one year; 2023 Q1: Specific R&D training for engineers for one year; 2024 Q1: Specific R&D training for engineers for one year; 2025 Q1: Specific R&D training for engineers for one year
2.3.5 Develop hazards maps (cartes d’aléas) | 2021 Q2: Strategic Plan; 2021 Q3: Strategic Plan; 2021 Q4: Development of climate hazards maps; 2022 Q1: Development of climate hazards maps; 2022 Q2: Development of climate hazards maps; 2022 Q3: Development of climate hazards maps; 2023 Q3: Maps update; 2024 Q3: Maps update; 2025 Q3: Maps update
2.3.6 Develop climate vulnerability maps based on the climate hazard maps | 2021 Q2: Strategic Plan; 2021 Q3: Strategic Plan; 2022 Q2: Development of climate risk vulnerabilitymaps; 2022 Q3: Development of climate risk vulnerabilitymaps; 2022 Q4: Development of climate risk vulnerabilitymaps; 2023 Q1: Development of climate risk vulnerabilitymaps; 2023 Q4: Maps update; 2024 Q4: Maps update; 2025 Q4: Maps update
Component 3
3.1 Production and dissemination of immediate CS improved at regional and national level
3.1.1 Improve the production and delivery of daily weather bulletin, seasonal forecasts, and agricultural advisories | 2021 Q2: End_user needs; 2021 Q3: Prototype of services; 2022 Q1: Operational services batch 1; 2022 Q4: User feedback Workshop; 2023 Q1: Operational services batch 2; 2024 Q1: User feedback Workshop; 2024 Q2: Operational services batch 3; 2025 Q2: User feedback Workshop; 2025 Q3: Improvment of services; 2025 Q4: Improvment of services
3.1.2 Strengthen early warning dissemination for key sectors and among the general public | 2022 Q1: Strategic planning; 2022 Q2: Strategic planning; 2022 Q3: User sensitization; 2022 Q4: User sensitization; 2023 Q1: User sensitization; 2023 Q3: User sensitization; 2023 Q4: User sensitization; 2024 Q1: User sensitization; 2024 Q3: User sensitization; 2024 Q4: User sensitization; 2025 Q1: User sensitization
3.2 Short- and long-term risk reduction and adaptation plans improved or developed based on high quality climate data, risk/vulnerability assessments and climate change projections (produced under Outcome 2)
3.2.1 Improve data sharing and coordination with emergency response plans for on-the-ground interventions at national and local levels | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Initial training for two or three months; 2023 Q1: Update of the training; 2024 Q1: Update of the training; 2025 Q1: Update of the training
3.2.2 Produce and/or update long term climate change adaptation plans responding to the needs of each country | 2021 Q3: Risk assessments; 2021 Q4: Risk assessments; 2022 Q3: Response action plan; 2023 Q1: Operational procedures effective; 2023 Q4: Update of plan; 2024 Q4: Update of plan
3.3 Training and improved communication with users and end-users of CS established
3.3.1 Train staff members of NHMS and in the RCC on how to package climate-related information in a user-friendly way | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Initial training for two or three months; 2023 Q1: Update of the training; 2024 Q1: Update of the training; 2025 Q1: Update of the training
3.3.2 Train knowledge brokers – including NGOs, red crescent/cross, local leaders and extension officers – and representatives of sectors in the GFCS areas (public and private organisations) on how to interpret and use CS for decision-making | 2021 Q3: Training Plan; 2021 Q4: Training Plan; 2022 Q1: Initial training for two or three months; 2023 Q1: Update of the training; 2024 Q1: Update of the training; 2025 Q1: Update of the training
3.3.2 Strengthen the User Interface Platform (UIP) |  | Technical study | Procurement of software for NMHS | Procurement of software for NMHS | Procurement of software for NMHS | Procurement of software for NMHS | Prototype of services |  | Operational services batch 1 |  | User feedback Workshop | Operational services batch 2 |  | User feedback Workshop | Operational services batch 3 |  |  | User feedback Workshop | Improvment of services
3.3.3 Support SWIOCOF to ensure the active participation of climate services users | 2021 Q3: SWIOCOF organization; 2022 Q3: SWIOCOF organization; 2023 Q3: SWIOCOF organization; 2024 Q3: SWIOCOF organization; 2025 Q2: Strategy to perennise SWIOCOF; 2025 Q3: SWIOCOF organization
Project Monitoring* | 2021 Q2: Inception Report; 2022 Q1: APR; 2023 Q1: APR; 2023 Q3: Interim Evaluation; 2024 Q1: APR; 2025 Q1: Completion Report; 2025 Q4: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.